## Main Req
[5 empty] | Successful | Non-Successful
| Original Scope | Implemented | Changes | Reasons for Change | Successful | Future Improvements
Landscape | Realistic, key buildings with interiors and/or exteriors, Qu’Appelle Valley area | Yes | Added more unique buildings, added a monument as well, landscape not as good as planned | Buildings and monuments for more related things and to make up for landscape | Successful | Better landscapes, better materials used, even more realistic environments
Non-Playable Characters (NPCs) | Main Ghost, Main Demon, Multiple NPCs with Varying AI | Yes | Added more characters throughout development | Added more to the game | Successful | Better AI, more unique looking characters, etc.
Dynamic Menu | Main Menu Changes as player progresses through game | Yes | Changed from a visually moving sky/weather to discrete visual changes (Four specific menu looks) | Difficulty in implementing day/night system, easiest to implement other things and still look good | Successful | Even more dynamic menus, weather, day/night, etc.
Multiple Items | Such as pistol, flashlight, etc. | Yes | Decided on flashlight, pistol, rifle, cross, and a knife | Keep it simple, 2 ranged weapons, 2 close combat, and 1 utility item | Successful | Better looking items, better animations for their use, etc.
Upgradable Items | Weapons, items, health, etc. can be upgraded | Yes | In the form of perks the user can upgrade by getting upgrade pickups. Upgrades have 0-6 choices | Made the most sense with how the game plays | Successful | Include more upgrades currently only for 4 catagories
Save/Load Game | The ability to save progress and return to that point without penalty | Yes | Saving and loading will return player to initial starting point of a level | Difficulty of saving player location and other variables | Successful | Multiple saves available, save player information so on load pickup exactly where left off
Start to Finish Aspects | Main menu, Opening, Main Game, Credits, Some Music & Sound Effects | Yes | Took out an "opening" scene, which would most likely be an animation | Time restrictions, very time consuming to implement, high amount of difficulty | Successful | Polish more to make the start to finish better, add cut scenese, etc.
Collectables | Letters, texts, messages, etc. Objects that relate to that area | Yes | Decided on 3 main collectables | Ease of creation, not overwhelming for player, etc. | Successful | Better models for the collectables
Side Objectives | A set of side objectives separate to the main objectives | Yes | Decided on having multiple side objectives, but at most one per level | Cut down on unneeded development, added more emphasis for story on collectables | Successful | More indepth side objectives, possibility of specific levels for some

## Sec Req
|  |  |  | Successful | Non-Successful | Not Finished | Not Attempted
| Original Scope | Implemented | Changes | Reasons for Change | Successful | Future Improvements | Notes
Easter Eggs & References | Either in game, something the player has to do, in texts, trophies, etc. | Started | N/A | N/A | Not Finished | N/A | Drafted up a multiple easter eggs and references that can be implemented
Trophies, Achievements, etc. | When the player completes specific tasks, give them the award | Started | N/A | N/A | Not Finished | N/A | Drafted up a table for this and have multiple ready to be implemented
Multiplatform | Playable on Xbox, Playstation, etc. | No | N/A | N/A | Not Attempted | N/A | Greatly out of scope and may not be implemented at all, even in future work
Name Game+ | Harder and different NPC AI Level changes | No | N/A | N/A | Not Attempted | N/A | Currently, level changes does not make sense nor does having different AI. No plans to implement this in future work
Music & Sound | Complete set of audio and more professionaly done | No | N/A | N/A | Not Attempted | N/A | Still plan to implement in future work, but prefer to get other objectives done first
Voice Acting | Voice acting done for NPCs, cutscenes, etc. | Yes | There was some voice recording for the audio log pickups | Audio logs is main collectable and needed voice recordings with them | Successful | More audio, professionaly done, done by more people, etc. | None
More Items | Add more items than the base ones done in main requirements | No | N/A | N/A | Not Attempted | N/A | Currently don't see a need to add more items
More Details | Better landscape, better attention to detail, better animations, etc. | No | N/A | N/A | Not Attempted | N/A | Details are always getting better with better knowledge of the engine and other softwar, and game development